## Project Info
Group ID | 18
Student ID | 230042129, 230042132, 230042157
Title | KidScribe
Brief Description | KidScribe is a tablet app that helps young children learn to write by hand using a stylus. Kids practice strokes, letters, words, and sentences. The app checks each letter and gives instant feedback. Parents can add words by taking photos of their child's own toys, and teachers can see which kids need extra help.
Summary
User stories | 33 total - 33 Done, 0 not done
Functional requirements | 24 (FR_1 to FR_24)
Unit tests | 80 total - 58 Pass (run automatically), 22 Not Run (to be done by hand on the emulator)
Notes
All 33 user stories are built in the app. The code passes 'flutter analyze' with no issues and the Android APK builds.
58 of the 80 unit tests were run automatically with 'flutter test unit_testing/test'. 129 Dart test cases ran and all 129 passed, so those 58 are marked Pass.
The other 22 tests need a real phone, so they are run by hand and are still 'Not Run'. Sign up and log in need Firebase's servers, reading handwriting needs Google's model on an Android device, reminders are sent by Android itself, toy words need the camera, and sync needs two devices.
The test code, the full run output, and the steps for the 22 by-hand tests are in the 'unit_testing' folder of the project.
US_28: the premium payment is a DEMO only. The app never asks for card details and no real money is taken. There is also a button to test a failed payment.
US_27: sync needs internet and a Firebase project. Sync only adds and joins data, so nothing is lost. Because of that, a child or a task deleted on one tablet comes back after the next sync.
FR_22, FR_23 and FR_24 (US_30 to US_33, tests T_69 to T_80) are new. They were added after the first SRS.

## User Stories
Serial | FR ID | Functional Requirement | User Story ID | US Title | As a (precise role) | I want (requirement) | So that (completion condition) | User Story | Acceptance Criteria | Priority | Status
1 | FR_1 | The system shall let parents and teachers create a new account. | US_1 | Parent creates an account | Parent | to create a parent account with my details | I can start using the app for my child | As a Parent, I want to create a parent account with my details, so that I can start using the app for my child. | - Full name and email address can be entered. - A password and a confirm password can be entered. - The account role is set as Parent. - The account is created after all fields are filled correctly. - If any required field is empty, the account is not created and a message is shown. - If the email is already used, an error message is shown. | High | Done
2 | FR_1 | The system shall let parents and teachers create a new account. | US_2 | Teacher creates an account | Teacher | to create a teacher account with my details | I can set up my class in the app | As a Teacher, I want to create a teacher account with my details, so that I can set up my class in the app. | - Full name, email, and school or institute name can be entered. - A password and a confirm password can be entered. - The account role is set as Teacher. - The account is created after all fields are filled correctly. - If the school or institute name is empty, the account is not created and a message is shown. | High | Done
3 | FR_1 | The system shall let parents and teachers create a new account. | US_3 | Check password format during sign up | Parent | to know if my password format is correct while I create my account | I can set a strong and valid password | As a Parent, I want to know if my password format is correct while I create my account, so that I can set a strong and valid password. | - The password rules are shown on the sign up screen. - The app checks the password while the user types. - A password with 8 or more characters, one capital letter, and one number is accepted. - If the password is shorter than 8 characters, an error message is shown. - If the password has no capital letter or no number, an error message is shown. - If the confirm password does not match, the account is not created. | High | Done
4 | FR_2 | The system shall let parents and teachers log in to their account. | US_4 | Parent logs in | Parent | to log in with my email and password | I can open my account safely | As a Parent, I want to log in with my email and password, so that I can open my account safely. | - Login screen asks for email and password. - Correct details log the parent in. - Parent stays logged in until they log out. - If the details are wrong, an error message is shown. - If the email or password field is empty, a message asks the parent to fill it. | High | Done
5 | FR_2 | The system shall let parents and teachers log in to their account. | US_5 | Teacher logs in | Teacher | to log in with my email and password | I can see my class safely | As a Teacher, I want to log in with my email and password, so that I can see my class safely. | - Login screen asks for email and password. - Correct details open the teacher view. - Teacher can log out safely. - If the details are wrong, an error message is shown. | High | Done
6 | FR_3 | The system shall let parents and teachers create and manage child profiles. | US_6 | Create a child profile | Parent | to create a profile for my child | the app can save each child's own progress | As a Parent, I want to create a profile for my child, so that the app can save each child's own progress. | - A new child profile can be added. - Child name and age can be entered. - More than one child can be added. - A profile can be edited or removed. - If the child name is empty, the profile is not saved and a message is shown. | High | Done
7 | FR_4 | The system shall let teachers create a class and add students. | US_7 | Create class and add students | Teacher | to create a class and add my students | I can follow all my students in one place | As a Teacher, I want to create a class and add my students, so that I can follow all my students in one place. | - A class can be created. - Students can be added to the class. - Each student shows in the class list. - A student can be removed from the class. - If the class name is empty, the class is not created and a message is shown. | High | Done
8 | FR_5 | The system shall let children practice basic strokes with a stylus. | US_8 | Practice basic strokes | Child | to practice basic strokes like lines, curves, and circles | I can get my hand ready before writing full letters | As a Child, I want to practice basic strokes like lines, curves, and circles, so that I can get my hand ready before writing full letters. | - Stroke practice screen can be opened. - Lines, curves, and circles can be traced. - The same stroke can be practiced again. - If nothing is drawn, a message asks the child to try the stroke. | High | Done
9 | FR_6 | The system shall let children practice writing letters from A to Z with a stylus. | US_9 | Write letters A to Z | Child | to write letters from A to Z with a stylus | I can learn how each letter is formed | As a Child, I want to write letters from A to Z with a stylus, so that I can learn how each letter is formed. | - A letter can be selected from A to Z. - The letter shape is shown as a guide. - The written letter is saved. - If the letter is written wrong, feedback shows what to fix. | High | Done
10 | FR_7 | The system shall check each written letter and show instant feedback. | US_10 | Get instant letter feedback | Child | to see if my letter is written correctly | I can fix my mistakes right away | As a Child, I want to see if my letter is written correctly, so that I can fix my mistakes right away. | - The app checks the letter after it is written. - A correct letter shows a success message. - Feedback appears right after writing. - A wrong letter shows what needs to be fixed. | High | Done
11 | FR_8 | The system shall let children practice writing common words. | US_11 | Write common words | Child | to write common words with a stylus | I can move from single letters to full words | As a Child, I want to write common words with a stylus, so that I can move from single letters to full words. | - A list of common words is shown. - Each word can be written with a stylus. - Finished words are saved. - If a letter in the word is wrong, feedback is shown and the word is not marked correct. | High | Done
12 | FR_9 | The system shall let children build sentences and learn basic grammar. | US_12 | Build a sentence | Child | to drag word cards to make a sentence | I can learn grammar through play | As a Child, I want to drag word cards to make a sentence, so that I can learn grammar through play. | - Word cards are shown on the screen. - Cards can be dragged to build a sentence. - A correct sentence shows a success message. - If the word order or spacing is wrong, the sentence is not accepted and feedback is shown. | Medium | Done
13 | FR_9 | The system shall let children build sentences and learn basic grammar. | US_13 | Learn punctuation and capital letters | Child | to use punctuation and capital letters | I can write proper sentences | As a Child, I want to use punctuation and capital letters, so that I can write proper sentences. | - Full stops and capital letters can be used. - The app shows where a capital letter is needed. - A correct sentence shows a success message. - If a capital letter or full stop is missing, the app shows what to fix. | Medium | Done
14 | FR_10 | The system shall guide children through five learning stages in order. | US_14 | Move through the learning stages | Child | to move through the five learning stages step by step | I can learn writing from easy to hard | As a Child, I want to move through the five learning stages step by step, so that I can learn writing from easy to hard. | - Five learning stages are shown in order. - The next stage opens after the current one is done. - The child's current stage is shown. - A later stage stays locked until the stage before it is finished. | High | Done
15 | FR_11 | The system shall provide a Letter Match game. | US_15 | Play Letter Match | Child | to match the same letters in a game | I can get better at knowing letters | As a Child, I want to match the same letters in a game, so that I can get better at knowing letters. | - Letter Match game can be started. - Same letters can be matched together. - The game gets harder as the child plays. - If two different letters are matched, no score is given and the child tries again. | Medium | Done
16 | FR_12 | The system shall provide a Letter Ninja timed game. | US_16 | Play Letter Ninja | Child | to write letters fast in a timed game | I can write more quickly and correctly | As a Child, I want to write letters fast in a timed game, so that I can write more quickly and correctly. | - Letter Ninja game can be started. - A timer runs during the game. - The app checks each written letter. - If the time runs out, the round ends and no reward is given. | Medium | Done
17 | FR_13 | The system shall provide a Free Writing activity on a blank screen. | US_17 | Free write on a blank screen | Child | to write letters freely on a blank screen | I can practice writing in my own way | As a Child, I want to write letters freely on a blank screen, so that I can practice writing in my own way. | - A blank writing screen can be opened. - Letters can be written freely with a stylus. - Badges are given for good writing. - If a letter is written wrong, it is marked wrong and feedback is shown. | Medium | Done
18 | FR_14 | The system shall give badges, streaks, and rewards to children. | US_18 | Earn badges and rewards | Child | to earn badges and rewards for my work | I feel happy and want to keep practicing | As a Child, I want to earn badges and rewards for my work, so that I feel happy and want to keep practicing. | - Badges are given for finished tasks. - A daily streak is counted for practice. - Earned badges are shown on a screen. - If a day of practice is missed, the streak count goes back to zero. | Medium | Done
19 | FR_15 | The system shall send daily practice reminders. | US_19 | Get a daily practice reminder | Parent | to get a daily reminder for my child to practice | my child keeps a daily practice habit | As a Parent, I want to get a daily reminder for my child to practice, so that my child keeps a daily practice habit. | - A daily reminder can be turned on. - The reminder time can be set. - The app sends a reminder at that time. - If the reminder is turned off, no reminder is sent. | Low | Done
20 | FR_16 | The system shall let parents add custom words using the toy camera. | US_20 | Add word from a toy photo | Parent | to take a photo of my child's toy and add it as a word | my child can practice words they care about | As a Parent, I want to take a photo of my child's toy and add it as a word, so that my child can practice words they care about. | - Camera can be opened inside the app. - A photo of a toy can be taken. - The toy word is added to the word list. - The new word shows up in games and practice. - If the photo is not clear, the word is not added and the app asks to take the photo again. | Medium | Done
21 | FR_17 | The system shall let parents set writing challenges for their child. | US_21 | Set a writing challenge | Parent | to set a small writing mission for my child | my child stays motivated to practice | As a Parent, I want to set a small writing mission for my child, so that my child stays motivated to practice. | - A challenge can be created by the parent. - A goal can be set, like write 5 words with letter A. - The child can see the challenge in the app. - The challenge is marked done when finished. - If no goal is set, the challenge is not created and a message is shown. | Medium | Done
22 | FR_18 | The system shall give teachers a class view of student progress. | US_22 | See struggling students | Teacher | to see which students need extra help | I can give help to the right kids | As a Teacher, I want to see which students need extra help, so that I can give help to the right kids. | - A class list is shown to the teacher. - Each student's progress is shown. - Students who are behind are marked. - The list updates as students practice. - If a student has no activity, they are shown as 'not started'. | High | Done
23 | FR_18 | The system shall give teachers a class view of student progress. | US_23 | Assign custom challenges | Teacher | to assign custom challenges to the class | I can give the right practice to students | As a Teacher, I want to assign custom challenges to the class, so that I can give the right practice to students. | - A challenge can be created by the teacher. - A goal can be set for the challenge. - The challenge is sent to the students. - Finished challenges are shown to the teacher. - If no goal is set, the challenge is not sent and a message is shown. | Medium | Done
24 | FR_18 | The system shall give teachers a class view of student progress. | US_24 | Export progress reports | Teacher | to export a student's progress report | I can use it in parent meetings | As a Teacher, I want to export a student's progress report, so that I can use it in parent meetings. | - A report can be created for each student. - The report can be exported from the app. - The report shows the progress details. - If the student has no activity, the report shows 'no activity yet'. | Low | Done
25 | FR_19 | The system shall track each child's progress and show reports to parents. | US_25 | View child's progress | Parent | to see my child's progress report | I know how my child is doing | As a Parent, I want to see my child's progress report, so that I know how my child is doing. | - A progress screen can be opened. - Weekly progress is shown. - Finished letters and words are listed. - Weak areas are shown clearly. - If the child has not practiced yet, the screen shows 'no progress yet'. | High | Done
26 | FR_20 | The system shall save data on the device and sync it across devices. | US_26 | Practice offline | Child | to practice even without internet | I can keep learning anywhere | As a Child, I want to practice even without internet, so that I can keep learning anywhere. | - Practice can be done without internet. - Written work is saved on the device. - Saved work is not lost when the app closes. - If there is no internet, practice still works and data is kept on the device. | Medium | Done
27 | FR_20 | The system shall save data on the device and sync it across devices. | US_27 | Sync progress across devices | Parent | to sync my child's progress on different devices | I can check the progress on any device | As a Parent, I want to sync my child's progress on different devices, so that I can check the progress on any device. | - Progress can be synced by the parent. - The same progress shows on all devices. - Synced data stays up to date. - If there is no internet, sync waits and a message is shown. | Low | Done
28 | FR_21 | The system shall provide premium features through a paid parent plan. | US_28 | Unlock premium features | Parent | to buy the premium plan in the app | I can use the extra premium features | As a Parent, I want to buy the premium plan in the app, so that I can use the extra premium features. | - The premium plan can be viewed in the app. - The premium plan can be bought. - Premium features open after payment. - Payment status is shown to the parent. - If the payment fails, premium stays locked and a message is shown. | Low | Done (demo payment)
29 | FR_21 | The system shall provide premium features through a paid parent plan. | US_29 | Use advanced reports and custom challenges | Parent | to use advanced reports and custom challenges | I can support my child's learning more deeply | As a Parent, I want to use advanced reports and custom challenges, so that I can support my child's learning more deeply. | - Advanced reports can be opened with premium. - Custom challenges can be made with premium. - Detailed progress charts are shown. - If the account is not premium, the feature is locked and an upgrade message is shown. | Low | Done
30 | FR_22 | The system shall let teachers and parents write feedback on a child's work. | US_30 | Write feedback on a child's work | Teacher | to write feedback on my student's work | the child knows what to practice next | As a Teacher, I want to write feedback on my student's work, so that the child knows what to practice next. | - A feedback box can be opened for a child. - Feedback can be written for the whole profile or for one finished letter. - Saved feedback is shown to the child. - Feedback can be removed. - If the feedback box is empty, nothing is saved and a message is shown. | Medium | Done
31 | FR_23 | The system shall let a time limit be set on an assigned task. | US_31 | Set a time limit on a task | Teacher | to set a deadline on the task I give | my students finish their work on time | As a Teacher, I want to set a deadline on the task I give, so that my students finish their work on time. | - A deadline can be set when the task is made. - The time left is shown to the student. - When the time is over, the task is closed and sent by itself. - The teacher can give more time later. - If no deadline is set, the task stays open. | Medium | Done
32 | FR_23 | The system shall let a time limit be set on an assigned task. | US_32 | Set a time limit on a challenge | Parent | to set a time limit on my child's writing challenge | my child practices regularly | As a Parent, I want to set a time limit on my child's writing challenge, so that my child practices regularly. | - A time limit can be set when the challenge is made. - The time left is shown to the child. - When the time is over, the challenge is closed. - The parent can give more time later. - If no time limit is set, the challenge stays open. | Medium | Done
33 | FR_24 | The system shall provide a timed test where no help is shown. | US_33 | Take a timed test | Child | to take a test with no help on the screen | my teacher can see what I can write on my own | As a Child, I want to take a test with no help on the screen, so that my teacher can see what I can write on my own. | - A test can be started from the task list. - The video, the guide and the numbered points are hidden during the test. - The timer starts when the child opens the test. - When the time is over, the test is locked and sent by itself. - The mark and the answer key are shown after the teacher gives the mark. | Medium | Done

## Unit Tests
Test ID | US ID | Test Case Title | Test Steps / Input | Expected Result | Type | How it was run | Status
T_1 | US_1 | Valid parent sign up | Name 'Rahim', email 'rahim@mail.com', valid password, role Parent | Account is created and the home screen opens | Positive | By hand on the emulator | Not Run
T_2 | US_1 | Empty required field | Name left empty, other fields filled | Account is not created and a 'please fill all fields' message is shown | Negative | By hand on the emulator | Not Run
T_3 | US_1 | Duplicate email | Email 'rahim@mail.com' that is already registered | Account is not created and an 'email already used' message is shown | Negative | By hand on the emulator | Not Run
T_4 | US_2 | Valid teacher sign up | Name, email, school name, valid password, role Teacher | Account is created and the teacher view opens | Positive | By hand on the emulator | Not Run
T_5 | US_2 | Missing school name | School or institute name left empty | Account is not created and an error message is shown | Negative | By hand on the emulator | Not Run
T_6 | US_3 | Password rules are visible | Open the password field on the sign up screen | The password rules text is shown on screen | Positive | By hand on the emulator | Not Run
T_7 | US_3 | Valid password accepted | Password 'Kidscribe1' | Password is accepted and no error is shown | Positive | Automatic (flutter test) | Pass
T_8 | US_3 | Password too short | Password 'Kid1' | Password is rejected and an 'at least 8 characters' message is shown | Negative | Automatic (flutter test) | Pass
T_9 | US_3 | No capital letter | Password 'kidscribe1' | Password is rejected and a 'need one capital letter' message is shown | Negative | Automatic (flutter test) | Pass
T_10 | US_3 | No number | Password 'Kidscribe' | Password is rejected and a 'need one number' message is shown | Negative | Automatic (flutter test) | Pass
T_11 | US_3 | Confirm does not match | Password 'Kidscribe1', confirm 'Kidscribe2' | Account is not created and a 'passwords do not match' message is shown | Negative | Automatic (flutter test) | Pass
T_12 | US_4 | Valid parent login | Correct email and password | Parent is logged in and the home screen opens | Positive | By hand on the emulator | Not Run
T_13 | US_4 | Wrong password | Correct email, wrong password | Parent is not logged in and an error message is shown | Negative | By hand on the emulator | Not Run
T_14 | US_4 | Empty field | Email left empty | A message asks the parent to enter the email | Negative | By hand on the emulator | Not Run
T_15 | US_5 | Valid teacher login | Correct email and password | Teacher view opens | Positive | By hand on the emulator | Not Run
T_16 | US_5 | Wrong details | Wrong password | Teacher is not logged in and an error message is shown | Negative | By hand on the emulator | Not Run
T_17 | US_6 | Add a child profile | Name 'Sara', age 5 | Profile is saved and shown in the profile list | Positive | Automatic (flutter test) | Pass
T_18 | US_6 | Empty name | Name left empty | Profile is not saved and a message is shown | Negative | Automatic (flutter test) | Pass
T_19 | US_6 | Remove a profile | Remove the 'Sara' profile | Profile is removed from the list | Positive | Automatic (flutter test) | Pass
T_20 | US_7 | Create class and add student | Class 'Class A', add student 'Sara' | Student shows in the class list | Positive | Automatic (flutter test) | Pass
T_21 | US_7 | Remove a student | Remove 'Sara' from the class | Student is removed from the list | Positive | Automatic (flutter test) | Pass
T_22 | US_7 | Empty class name | Class name left empty | Class is not created and a message is shown | Negative | Automatic (flutter test) | Pass
T_23 | US_8 | Trace a stroke | Draw a straight line on the stroke screen | Stroke is accepted and can be practiced again | Positive | Automatic (flutter test) | Pass
T_24 | US_8 | No drawing | Leave the stroke screen without drawing | A message asks the child to draw the stroke | Negative | Automatic (flutter test) | Pass
T_25 | US_9 | Write a letter | Select 'A' and write it on the guide | Letter is saved and marked correct | Positive | Automatic (flutter test) | Pass
T_26 | US_9 | Wrong letter shape | Write a messy 'A' far from the guide | Feedback shows what to fix | Negative | Automatic (flutter test) | Pass
T_27 | US_10 | Correct letter feedback | Write a clear 'B' | A success message is shown | Positive | Automatic (flutter test) | Pass
T_28 | US_10 | Wrong letter feedback | Write an unclear 'B' | Feedback shows what needs to be fixed | Negative | Automatic (flutter test) | Pass
T_29 | US_11 | Write a word | Write 'cat' correctly | Word is checked, marked correct, and saved | Positive | By hand on the emulator | Not Run
T_30 | US_11 | Wrong letters in word | Write 'cot' when the target is 'cat' | Word is not marked correct and feedback is shown | Negative | By hand on the emulator | Not Run
T_31 | US_12 | Build a correct sentence | Drag cards to make 'The cat is big' | A success message is shown | Positive | Automatic (flutter test) | Pass
T_32 | US_12 | Wrong word order | Drag cards to make 'big cat The is' | Sentence is not accepted and feedback is shown | Negative | Automatic (flutter test) | Pass
T_33 | US_13 | Correct punctuation | Write 'The cat is big.' with a capital and a full stop | A success message is shown | Positive | Automatic (flutter test) | Pass
T_34 | US_13 | Missing capital letter | Write 'the cat is big.' | The app shows that a capital letter is needed | Negative | Automatic (flutter test) | Pass
T_35 | US_14 | Unlock next stage | Finish Stage 1 | Stage 2 opens | Positive | Automatic (flutter test) | Pass
T_36 | US_14 | Locked stage | Try to open Stage 3 before Stage 2 is done | Stage 3 stays locked | Negative | Automatic (flutter test) | Pass
T_37 | US_15 | Correct match | Match 'A' with 'A' | The score goes up | Positive | Automatic (flutter test) | Pass
T_38 | US_15 | Wrong match | Match 'A' with 'B' | No score is given and the child can try again | Negative | Automatic (flutter test) | Pass
T_39 | US_16 | Fast correct writing | Write the letter correctly before the timer ends | A reward is given | Positive | By hand on the emulator | Not Run
T_40 | US_16 | Time runs out | Do not finish the letter before the timer ends | The round ends and no reward is given | Negative | By hand on the emulator | Not Run
T_41 | US_17 | Free write correctly | Write clear letters on the blank screen | Letters are checked and a badge is given | Positive | By hand on the emulator | Not Run
T_42 | US_17 | Wrong letter | Write an unclear letter | The letter is marked wrong and feedback is shown | Negative | By hand on the emulator | Not Run
T_43 | US_18 | Earn a badge | Finish a practice task | A badge is given and shown | Positive | Automatic (flutter test) | Pass
T_44 | US_18 | Streak reset | Miss one day of practice | The streak count goes back to zero | Negative | Automatic (flutter test) | Pass
T_45 | US_19 | Reminder is sent | Turn on the reminder and set it to 6 PM | A reminder is sent at 6 PM | Positive | By hand on the emulator | Not Run
T_46 | US_19 | Reminder turned off | Turn off the reminder | No reminder is sent | Negative | By hand on the emulator | Not Run
T_47 | US_20 | Add a toy word | Take a clear photo of a toy dinosaur | The word 'dinosaur' is added and shows in games | Positive | By hand on the emulator | Not Run
T_48 | US_20 | Unclear photo | Take a blurry photo | No word is added and the app asks to retake the photo | Negative | Automatic (flutter test) | Pass
T_49 | US_21 | Create a challenge | Set goal 'write 5 words with letter A' | The child can see the challenge | Positive | Automatic (flutter test) | Pass
T_50 | US_21 | Complete a challenge | Child finishes the 5 words | The challenge is marked done | Positive | Automatic (flutter test) | Pass
T_51 | US_21 | Empty goal | Try to create a challenge with no goal | The challenge is not created and a message is shown | Negative | Automatic (flutter test) | Pass
T_52 | US_22 | Struggling student marked | A student who is behind on practice | The student is marked in the class list | Positive | Automatic (flutter test) | Pass
T_53 | US_22 | List updates | A marked student does more practice | The student's progress updates in the list | Positive | Automatic (flutter test) | Pass
T_54 | US_22 | No activity | A student who has not started | The student is shown as 'not started' | Negative | Automatic (flutter test) | Pass
T_55 | US_23 | Assign a challenge | Create a class challenge with a goal | The challenge is sent to the students | Positive | Automatic (flutter test) | Pass
T_56 | US_23 | Empty goal | Try to assign a challenge with no goal | The challenge is not sent and a message is shown | Negative | Automatic (flutter test) | Pass
T_57 | US_24 | Export a report | Export the report for an active student | A report file with progress details is created | Positive | Automatic (flutter test) | Pass
T_58 | US_24 | No activity report | Export the report for a student with no activity | The report shows 'no activity yet' | Negative | Automatic (flutter test) | Pass
T_59 | US_25 | View progress | Open the progress screen for an active child | Weekly progress and weak areas are shown | Positive | Automatic (flutter test) | Pass
T_60 | US_25 | No progress yet | Open the progress screen for a new child | The screen shows 'no progress yet' | Negative | Automatic (flutter test) | Pass
T_61 | US_26 | Practice with no internet | Turn off internet and write letters | Work is saved on the device | Positive | Automatic (flutter test) | Pass
T_62 | US_26 | Reopen the app | Close and open the app again | The saved work is still there | Positive | Automatic (flutter test) | Pass
T_63 | US_27 | Sync across devices | Sync on the tablet, then open the app on the phone | The same progress shows on the phone | Positive | By hand on the emulator | Not Run
T_64 | US_27 | Sync with no internet | Try to sync with no internet | Sync waits and a message is shown | Negative | By hand on the emulator | Not Run
T_65 | US_28 | Buy premium | Complete the payment for the premium plan | Premium features open | Positive | Automatic (flutter test) | Pass
T_66 | US_28 | Failed payment | Payment fails during checkout | Premium stays locked and a message is shown | Negative | Automatic (flutter test) | Pass
T_67 | US_29 | Open advanced report | A premium parent opens the advanced report | Detailed charts are shown | Positive | Automatic (flutter test) | Pass
T_68 | US_29 | Non-premium blocked | A free parent tries to open the advanced report | The feature is locked and an upgrade message is shown | Negative | Automatic (flutter test) | Pass
T_69 | US_30 | Write feedback on the profile | Write 'Great work on A' for the whole profile | The feedback is saved and shown to the child | Positive | Automatic (flutter test) | Pass
T_70 | US_30 | Write feedback on one letter | Write feedback on the finished letter A | The feedback is shown for letter A | Positive | Automatic (flutter test) | Pass
T_71 | US_30 | Empty feedback | Leave the feedback box empty and press save | Nothing is saved and a message is shown | Negative | Automatic (flutter test) | Pass
T_72 | US_31 | Deadline is shown | Teacher gives a task with a 1 day deadline | The student sees the time left on the task | Positive | Automatic (flutter test) | Pass
T_73 | US_31 | Task closes at the deadline | Let the deadline pass without finishing the task | The task is closed and sent by itself | Negative | Automatic (flutter test) | Pass
T_74 | US_31 | Give more time | Teacher presses 'Give more time' on a closed task | The task opens again with more time | Positive | Automatic (flutter test) | Pass
T_75 | US_32 | Parent sets a time limit | Parent gives a challenge with a 2 day limit | The child sees the time left on the challenge | Positive | Automatic (flutter test) | Pass
T_76 | US_32 | Challenge closes at the limit | Let the time limit pass | The challenge is closed and cannot be done | Negative | Automatic (flutter test) | Pass
T_77 | US_33 | No help during a test | Open a 10 minute test | No video, no guide and no numbered points are shown | Positive | Automatic (flutter test) | Pass
T_78 | US_33 | Test is sent when time is over | Let the test timer reach zero | The test is locked and sent by itself | Negative | Automatic (flutter test) | Pass
T_79 | US_33 | Mark and answer key | Teacher gives a mark and an answer key | The child sees the mark and the answer key | Positive | Automatic (flutter test) | Pass
T_80 | US_33 | Test clock starts on open | Open the test for the first time | The timer starts counting down | Positive | Automatic (flutter test) | Pass